## ADDITIONAL SAFETY AREAS
ADDITIONAL SAFETY AREAS (ASA)
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Impaired Driving Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSIP 21-24 Implementation Plan | RTSP( COGs) | Summit |  | Near-term | Mid-term | Long-term
Areas identified to be comprehensive and direct efforts to achieving zero fatalities for all users. | Unlicensed drivers: identified in crash report as "Not Licensed". | Addressing unlicensed drivers. Look into user breakdown. | In SHSP. | [6 empty] | X |  | need more data regarding unlicensed drivers
|  | Data improvements and analysis to understand why drivers are commonly not getting licensed and causes for this. | CT Safety Research Center/CT Safety Analysis Methods |  | X |  |  |  |  | X |  | need time to determine data needs and perform analysis
|  | Collaboration among partners. | Identifying updates to the driver's test coming into effect. | X |  |  |  | X | X |  |  | Reach out to DMV to gather information on updated to the driver's test coming into effect.
|  |  | Addressing unlicensed drivers that are repeat offenders. | X |  |  |  | X |  |  | X | Explore why drivers are operating vehicles unlicensed.
|  |  | Ask DMV about their current process for handling repeat offenders. | X |  |  |  |  | X |  |  | Need to gather info
| Hit-and-Runs: identified in the crash report as "true" in the "hit-and-run" status. | Improvements in data and analysis needed to better understand why, where and when hit-and-run crashes are occurring and potential causes. | CT Safety Research Center/CT Safety Analysis Methods |  | X |  |  |  |  | X |  | information being gathered; need time to analyze
|  |  | Identify "hot spot" locations for hit and run crashes and what mitigation efforts can be used. | X | [5 empty] | X |  | need time to gather information
|  |  | Perform cluster analysis for "hot spot" locations. | X | [5 empty] | X |  | need time to gather information
|  |  | Analyzing the correlation between hit-and-run crashes and impaired driving. |  |  |  | X |  |  | X |  | data available, need time to analyze
|  | Addressing aggressive or speeding drivers and hit-and-runs. | In SHSP. | [8 empty] | data available, need time to analyze
|  | Enforcement increases. | Increase enforcement to reduce hit-and-runs. | X |  |  |  | X | X |  |  | Identify hot-spot areas for targeted enforcement.
|  |  | Increased penalties for hit-and-run drivers | X | [6 empty] | X | explore legislation
|  |  | Speed enforcement on HRRR |  | X |  |  |  |  | X
|  | Automated enforcement - red light running cameras. | Use of automated enforcement for red light running. | X | [5 empty] | X |  | overlaps with other EAs; program in place for municipalities
|  | Collaboration among partners. | In SHSP. | [6 empty] | X |  | explore ways to increase collaboration
| Work zones: identified as "yes" based on the "work zone related" field in the crash report. | Increased awareness campaigns. | Provide driver education for safely navigating work zones. |  |  |  | X |  |  | X |  | develop and increase public messaging
|  | Increased enforcement and roadway safety audits (RSAs) at work zones. | In SHSP. | [6 empty] | X |  | automated enforcement in work zones underway; RSAs being done currently in non work zones
|  | Increased data analysis on various road types. | Explore percentage of work zones by road type and identify crash trends; consider percentage of KA's by road type | X |  |  |  | X |  | X |  | needs further data collection and analysis
|  | Smart work zones. | Implementation of smart work zones. | X |  |  |  | X | X |  |  | currently underway; consider more implementation
|  | Continued utilization of the Operation Big Orange work zone safety program. | Maintaining consistent signing and pavement markings in work zones. | X |  |  | X | X | X |  |  | continue to support
|  | Work zone safety and mobility process reviews and annual work zone reports. | In SHSP. | [5 empty] | X |  |  | reviews being done - need to review data and possible implementation ideas from the reports
|  | Continued study of the effects of (and possibly expand) on automated work zone speed cameras. | Integration of automated enforcement into work zones. | X |  |  |  |  | X |  |  | Pilot program report finalized and permanent program underway.
| Commercial vehicles: defined where the "body type" field in the crash report is "medium/heavy trucks more (than 10,000 lbs. (4,536 kgs)", "motor home", "school bus", "transit bus", "motor coach", or "other bus". | Using strategies outlined in the Annual Connecticut Commercial Vehicle Safety Plan. | Explore crash data to identify what is causing crashes and how they can be mitigated. | X |  |  |  | X |  | X |  | needs data collection and analysis
|  |  | Over-height detection and alert system integration for passings with low clearance. |  |  |  | X |  | X |  |  | systems are available; need time to determine more widespread installation
|  | Hazmat identification. | Hazmat vehicle identification in crash data. | X | [6 empty] | X | needs further information gathering including identifying more data from crash reports
|  | Parking on shoulders, ramps - increased enforcement. Increasing awareness of areas commercial vehicles can safely park. | Mapping to identify safe areas for CMV parking; parking study analysis | X |  |  |  | X |  | X |  | study is ongoing; need time to do analysis
|  | Awareness of steep slopes - increased signage. | Warning signs for CMVs in areas with high grades. | X |  |  |  | X |  | X |  | need to gather grade data and analyze need; consider sections of eastern I-84
| Older drivers and older pedestrians: Older Drivers and Older Pedestrians refer to crashes involving a pedestrian or driver that is 65 years of age or older | Consider strategies shown in the FHWA Handbook for Designing roadways for the Aging Population. https://safety.fhwa.dot.gov/older_users/fhwasa15088/ | Explore what other states are doing for older driver retraining. | X | [5 empty] | X |  | need time to gather information
|  | Connecticut will consider effective strategies for reducing older driver and pedestrian fatalities and serious injuries. | Explore number of drivers licenses issues by age group & investigate crash trends. | X |  |  |  | X |  | X |  | need time to collect and analyze data
|  |  | Consider formal support of stricter CTDMV policy of license renewal for senior drivers and consider mandatory in person tests with vision exam for drivers 65 years and older. |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  | X |  |  | X | need time to gather information and determine if this feasible and if so, time to develop legislation
|  |  | More effective and accessible public transportation for the elderly (on-demand transit). |  |  |  | X |  |  |  | X | some programs existing; need time to investigate effectiveness
|  |  | Require eye and hearing exams prior to issuing license renewal. |  |  |  | X |  |  |  | X | needs time to investigate
|  |  | Assistance in getting older drivers off the road who are no longer fit to drive. |  |  |  | X |  |  |  | X | needs time to investigate
|  |  | Coordinate with multiple agencies including various local chapters of the YMCA, the Connecticut Association of Senior Center Personnel, and local police/fire departments and hospitals to address older driver challenges and general safety. |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | needs time to investigate and develop further
|  |  | Using earned media outlets to promote NHTSA’s DriveWell Toolkit to aid older drivers. |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | needs time to develop promotion
|  |  | Continue to promote alternative ways for older people to get around and promote Know How to Go website, dial-a-ride through NE CT Transit District, and reference the 2016 Transportation Guide for Northwestern CT. |  |  | X (CRCOG, METRO, NVCOG, RIVERCOG, SCCOG, NECCOG, NHCOG, WESTCOG) |  |  |  | X |  | needs time to develop promotion
|  | Encouraging/promoting older drivers course offered by AARP. | Explore mandatory training for all older drivers over a certain age. | X |  |  |  | X |  |  | X | AARP offers a 4-hour safety course taught in every state & is required to distribute 4-page handout on driver safety; needs time to further investigate
|  |  | Encourage older drivers to use AARP Smart Driver Course, available online or in classrooms in the region, and spread awareness on AARP courses available. | X |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | Continue to support. Note AARP offers a 4-hour safety course taught in every state & is required to distribute 4-page handout on driver safety
| Railway-Highway Grade Crossings | Assessment of longer-term crash potential | In SHSP. | [7 empty] | X | needs further investigation
|  | modernize railroad crossings | at-grade crossing upgrades |  | X |  |  |  | X |  |  | projects underway
|  | Proactive methods to identify potential locations for improvements | Addition of edgelines and centerlines at RR crossings. | X |  |  |  |  | X |  |  | being implemented in projects
|  | Analyze opportunities for closure of grade crossing improvements | In SHSP. | [5 empty] | X |  | X | improvements done in projects; closure opportunities will take further investigation and coordination
| Pedal Cyclists: Pedal cyclist crashes are those where the “person type” field in the crash report is marked as "Bicyclist" or "Other Cyclist". Reflects bicycle and motor vehicle collisions but does not include collisions with another bicycle or pedestrian. | Collaborate with partners. | Safe Routes to School Program (SRTS) |  | X |  |  |  | X |  |  | continue to support
|  |  | Safety circuit rider program. |  | X |  |  |  | X |  |  | continue to support
|  | Increase lighting at intersections with high pedestrian volumes; Statewide illumination study being done by CTDOT (HSIP) | Analyze illumination study addressing visibility for vulnerable road users (VRUs) | X |  |  |  | X |  | X |  | study underway
|  | Looking at overlaps with roadway data. | In SHSP. | [6 empty] | X |  | needs time for further data analysis
|  | User/type breakdown of crashes. | Provide a gender/age/ability breakdown of cyclist crashes. | X | [6 empty] | X | needs further investigation
|  | Implement the CT Active Transportation Plan | In SHSP. | [6 empty] | X |  | recommendations under consideration
|  | Updates to pedestrian barrier spec to better match MUTCD, meets ADA requirements. | In SHSP. | [5 empty] | X |  |  | needs further investigation
|  | Updated directive to the complete streets plan. | Utilize the complete streets directive to implement Pedalcyclist accessibility and illumination improvements. | X |  |  |  | X | X |  |  | Directive complete; needs time for implementation in projects
|  |  | Integrate protected and connected infrastructure for bicyclists. |  |  |  | X |  |  |  | X | needs time to further investigate and implement
| Younger drivers: Younger Driver crashes are defined where the age of the driver is between (and including) 15 to 20 | Use a variety of 4E strategies such as high school events, driver training enhancements and mitigating risky driving behavior | Explore how other states are educating younger drivers. | X |  |  |  | X |  | X |  | needs time to gather information
|  |  | Provide in-person, accessible driver training courses for young drivers. | X |  |  |  | X |  | X |  | needs time and support to develop
|  |  | Study effectiveness of Driver Training Courses in CT. | X |  |  |  | X |  |  | X | needs time to further investigate and collect data
|  |  | Investigate effectiveness of laws for Younger Drivers in Reducing Crashes. | X |  |  |  | X |  | X |  | needs time to collect data
|  |  | Increase equity of driver education classes. | X | [5 empty] | X |  | needs time to further investigate
|  |  | Ensure online driver education classes are interactive and/or incorporate in-person portion(s). | X | [5 empty] | X |  | needs time to investigate
|  |  | Continue regional support for statewide GDL programs. |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG) |  |  | X |  |  | continue to support - need more legislation?
|  |  | Regional education and enforcement of young driver laws, including the State's .02 BAC laws for teens by organizing and conducting high-visibility enforcement campaigns. |  |  | X (CRCOG, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG) |  |  |  | X |  | continue to support; needs more staffing for HVE
|  |  | Explore the possibility of a license plate decal to identify motorists in the GDL program, so that law enforcement can more readily distinguish them. |  |  | X (CRCOG, NECCOG, NHCOG, RIVERCOG, SCCOG) |  |  |  |  | X | needs further investigation and policy consideration
|  |  | Coordinate young driver messages with multiple agencies in Spanish and English at DMV offices, auto insurance agencies, AAA CT Chapters, State and local law enforcement agencies, Emergency Management Services, public and private schools, local chapters of the YMCA, and the State Board of Education. |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG) |  |  |  | X |  | needs further investigation to implement with multiple agencies
|  |  | Conduct regional enforcement of young driver laws, including Zero Tolerance law by organizing and conducting HVE campaigns. |  |  | X (METRO) |  |  |  | X |  | needs more staffing for HVE
|  |  | Continue to promote IMPACT Programs which offer teen driving safety programs to high schools, hospitals, religious organizations, and other communities at no cost. In the Greater Bridgeport Region, one Victim Impact Panel occurs in Stratford: https://www.maddvip.org/ |  |  | X (METRO, NHCOG, SCCOG) |  |  | X |  |  | continue to support; needs time to promote
|  |  | Ensuring out of state license transfers receive education. |  |  |  | X |  | X |  |  | already being done
|  |  | Research further details on driver training in CT and when the shift to remove from public schools took place. | X | [5 empty] | X |  | needs further investigation; also discussed with Vision Zero
| Tribal-Owned Roadways: There are 30 miles of tribal roadways in Connecticut, but the exact location of them is unknown. | Increased tribal engagement | In SHSP. | [7 empty] | X | tribal engagement at Steering Committee level; need to do more engagement for future meetings
|  | Identification and subsequent safety analysis of the tribal roadways | In SHSP. | [7 empty] | X | needs time for further investigation if supported
| Wrong way drivers: Wrong way driving (WWD) happens when a driver, inadvertently or deliberately, drives in the opposite direction of traffic flow. When this happens on a high speed divided highway (freeway, expressway, or Interstate highway), head-on or opposite direction sideswipe crashes may occur resulting in serious injuries and fatalities. | Investigate new strategies | WWD education campaign. |  | X |  |  |  | X |  |  | underway
|  | Continue to implement infrastructure strategies to reduce WWD | Continue to implement infrastructure improvements such as replacement/installation of one-way signs & installation of pavement markings. | X | X |  |  | X | X |  |  | projects underway
|  |  | Increase WWD detection on highway on/off ramps. | X |  |  |  | X | X |  |  | program underway
|  |  | Integration of wrong way driver detection that notifies the police department. |  |  |  | X |  |  | X |  | pilot underway; needs further information for more widespread implementation
| Traffic Incident Management: Additional data collection and analysis may be needed to address all 3 of the FHWA TIM performance measures: incident clearance time, roadway clearance time and secondary crashes. Consider forming a group to determine approaches for obtaining the data to calculate the metrics and assess the ambiguity of secondary crash metrics to improve TIM. The reduction of secondary crashes is a high priority for the CT SHSP. | Educate emergency responders on the importance of incident management and quick clearance practices. | Continue to conduct public awareness programs for effective on scene TIM by road users |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support; need to further investigate widespread program
|  | Identify appropriate strategies to improve incident response. | CHAMP safety service patrol/ support the State Farm Safety patrol program |  | X | X (CRCOG, NECCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  | X |  |  | program in place
|  |  | Fatality Analysis Reporting System (FARS) |  | X |  |  |  | X |  |  | already being done
|  |  | Conduct after action reviews to improve response and scene management. |  |  | X (CRCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | needs further development
|  |  | Continue collaborating with CTDOT to implement ITS to update the freeway traffic management system and improve incident management efforts. |  |  | X (CRCOG, METRO, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support
|  |  | Continue to research the benefits and impacts of providing a regional approach to operating and maintaining local traffic signal systems. |  |  | X (CRCOG, NECCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | needs further investigation
|  |  | Continue to implement the goals from the ITS Strategic Plan for the Capitol Region and the goals in the LRTP. |  |  | X (CRCOG, NECCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support
|  |  | Provide Intelligent Transportation System (ITS) technology to reduce response times. |  |  | X (METRO) |  |  |  | X |  | needs time to investigate further
|  |  | Continue to install reference markers on highways every 0.2 miles to improve Emergency Response Times |  |  | X (METRO, NHCOG) |  |  | X |  |  | ongoing as signing projects implemented
|  |  | Reduce incident duration, which is achieved through: 1. Reducing the time to detect incidents. 2. Initiating an expedient and appropriate response. 3. Clearing the incident as quickly as possible. |  |  | X (METRO, NHCOG) |  |  |  | X |  | continue to support
|  |  | Promote best practices for traffic incident management and provide access to ITS tools. |  |  | X (METRO, NHCOG) |  |  |  | X |  | continue to support and needs time to promote
|  |  | Promote the safety of motorists, crash victims, and incident responders by reducing secondary crashes and associated fatalities and serious injuries. | X |  | X (NHCOG) |  |  |  | X |  | needs time to further investigate secondary crash data
|  |  | Regionally investigate investing in installing visual message boards along limited access highways within NHCOG. |  |  | X (NHCOG) |  |  |  | X |  | specific to one region; needs time to investigate development in others as well
|  |  | Identify staffing needs and training resources for CT DOT staff and emergency responders. |  |  | X (NHCOG) |  |  |  | X |  | needs time for further investigation
|  | Continue to raise awareness to the State of Connecticut Incident Management Policy and the Connecticut Quick Clearance Policies. | Continue the planning, implementation, and coordination of activities such as the adoption of a Unified Response Manual, updating of diversion plans, TIM training, and participation in the FHWA annual TIM Self-Assessment. Also, work on the development and implementation of a public awareness campaign for motor vehicle laws relating to highway incidents, such as the “Move It” and the “Move Over." |  |  | X (CRCOG, NECCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  | X |  |  | continue to support and needs time to promote
|  |  | Support the CT SHSP objective to establish a statewide TIM program, with a lead agency to administer clearly defined responsibilities that meet the requirements of the National Incident Management System (NIMS). |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support
|  |  | Continue to support the CT Travel Smart website and to promote this resource regionally through media and public outreach campaigns. |  |  | X (CRCOG, METRO, NECCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support and needs time to promote
|  |  | Improve CTDOT and MetroCOG communications regarding TIM coordination and training opportunities. |  |  | X (METRO) |  |  |  | X |  | specific to one region; needs time to investigate if needed in others as well
|  |  | Work with CTDOT and the Federal Highway Administration to develop a regional partnership that would coordinate with public and private sector partners to address traffic incident safety, operations, and trainings. Collaborate with CRCOG’s traffic incident management coalition to learn best practices (https://crcog.org/traffic-incident-management-update/) |  |  | X (METRO) |  |  |  | X |  | needs further investigation
|  |  | Augment CT DOT and NHCOG communication regarding coordination, training. |  |  | X (NHCOG) |  |  |  | X |  | specific to one region; needs time to investigate if needed in others as well
|  | Investigate opportunities to improve the collection and reporting of secondary crash information. | More data fields in the crash report. | X | [5 empty] | X |  | committee is working on updating crash reporting fields
|  |  | Include Weather Responsive Traffic Management (WRTM) strategies, such as Road Weather Information Systems (RWIS). |  |  | X (CRCOG, METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support
|  |  | Support the development and tracking of TIM performance metrics following national standards and definitions. |  |  | X (METRO, NECCOG, NHCOG, NVCOG, RIVERCOG, SCCOG, WESTCOG) |  |  |  | X |  | continue to support; needs further development
|  |  | Conduct After-Action Reviews to improve response and scene management. |  |  | X (METRO, NHCOG, NVCOG) |  |  |  | X |  | continue to support; needs further development
|  |  | Support a statewide NIMS-based Unified Response Manual (URM). |  |  | X (NHCOG) |  |  |  | X |  | continue to support
|  |  | Evaluate expansion of ITS infrastructure to additional regional corridors based on prioritized need. |  |  | X (NHCOG) |  |  |  |  | X | needs further development
HOW?
HOW?
WHEN?

## x2 (hidden)
STRATEGY 4: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x3 (hidden)
STRATEGY 6: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x4 (hidden)
STRATEGY 9: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x5 (hidden)
STRATEGY 10: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x6 (hidden)
STRATEGY 11: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?