## IMPAIRED DRIVING
BEHAVIORAL EA: IMPAIRED DRIVING
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Impaired Driving Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeframe |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSP 21-23 | Vision Zero | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of impaired driving fatalities and serious injuries to less than 233 by 2026. | Reduce excessive and underage drinking. | Support media buys for increasing public awareness and education to reduce impaired driving. | Consider mandatory trainings for servers and bartenders to minimize overserving. | X |  |  |  |  | X |  |  | X | Collaborate with responsibility.org; would need legislative bill
|  |  | Support Mothers Against Drunk Driving (MADD) CT chapter’s outreach and education efforts, including the Victim Impact Panels that occur at University of Hartford |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | needs further investigation on how to support
|  |  | Drive Safe Connecticut Media Partnership |  | X |  |  |  |  | X |  |  | Partnership with Fox 61 Local News;
|  |  | Cannabis Impairment Awareness Media Campaign |  | X |  |  |  |  | X |  |  | continue to support; already being done
|  |  | GDL/Teen Driving Education and Outreach Initiatives such as developing a website serving as an online resource for teen drivers |  | X | [5 empty] | X |  | needs further investigation on how to support and lead
|  |  | Virtual reality experience simulating the consequences of drunk driving. | X | [7 empty] | X | needs time to develop
|  |  | Interactive online quizzes to educate people about the effects of alcohol and impaired driving. | X | [7 empty] | X | needs time to develop
|  |  | Increasing insurance or other incentives if a person takes driver training courses | X |  |  |  | X |  |  | X |  | Needs further investigation as well as statutory/regulatory changes.
|  |  | Targeted educational and awareness campaigns to demographics with high impaired driving instances, while considering equitable practices |  |  |  |  | X |  |  | X |  | needs further investigation and data collection
|  | Continue to engage high school students in educational events an peer-to-peer activities. | Underage Alcohol Enforcement Grant Program which provides funding for municipal law enforcement agencies |  | X |  |  |  |  | X |  |  | already being done
|  |  | Choices Matter Impaired Driving Program featuring Chris Sandy focusing on spreading impaired driving messages throughout schools in the state |  | X |  |  |  |  | X |  |  | featuring Chris Sandy? Already being done
|  |  | Student-led Webinars focusing on the dangers of underage drinking | X | [7 empty] | X | needs further investigation to develop
|  |  | Arts competitions where students can express their understanding of risks associated with underage drinking (In SHSP) | [7 empty] | X |  | needs further investigation to develop
|  | Develop safe-ride community partnerships. | Support policies and programs that increase the availability, convenience, affordability, and safety of transportation alternatives for drinkers who may drive (especially during night time and weekend hours). |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  | X |  | X |  | some being done already; some need further investigation; funding sources to be identified
|  |  | Local Business Sponsorships to offer free or discounted taxi services. | X | [6 empty] | X |  | need to reach out to get support and develop program
|  |  | Community Volunteer Driver Programs | X | [7 empty] | X | needs further investigation
|  |  | Night Bus Services offered by local transit authority on weekends | X | [7 empty] | X | needs further investigation
|  |  | Providing ride-share vouchers through awareness campaigns |  |  |  |  | X |  | X |  |  | has been done; need to investigate/determine funding to do more
|  | Seek partnerships with ride-share programs. | Geo-targeted Promotions offered during "high risk times" in popular nightlife areas | X | [6 empty] | X |  | needs further investigation
|  |  | Ride-share Credit for High-risk Groups | X | [6 empty] | X |  | needs further investigation
|  |  | Educational Pop-Ups | X | [6 empty] | X |  | needs further investigation
|  |  | Providing ride-share vouchers through awareness campaigns |  |  |  |  | X |  | X |  |  | vouchers have been done on a limited basis; needs further investigation on how to do more; increase funding and determine effectiveness
|  |  | Promote use of ride shares as an alternative travel method |  |  |  |  | X |  |  | X |  | needs further investigation and development
|  | Improve access to transit. | Encourage the use of public transportation as a safe and reliable form of travel. Promote HARTransit, Norwalk Transit District, and CTtransit (Stamford Division) services to all users. In addition, promote the use of public transportation as a solution for substance-impaired driving. |  |  |  | X (WEST) |  |  |  | X |  | needs further development for additional public transportation throughout state
|  |  | Extend public transit hours on weekends and holidays | X | [6 empty] | X |  | needs further investigation
|  |  | Fare-free zones where public transit is discounted or free to promote usage | X | [6 empty] | X |  | needs further investigation
|  |  | Mobile apps that allow people to easily find and use public transit | X | [6 empty] | X |  | further development needed
|  |  | Promote use of transit as an alternative travel method |  |  |  |  | X |  |  | X |  | educational resources need further development
|  | Expand screening, brief intervention, and referral to treatment. | Support implementation of pilot Oral Fluids Testing programs. | X |  |  |  |  | X |  | X |  | To address drug impaired driving and poly-drug usage; needs further development including policy development
|  |  | Telehealth Services offering virtual screening and consultations | X | [6 empty] | X |  | needs further investigation
|  |  | Mobile Clinics in high risk areas to offer on the spot screenings and interventions | X | [7 empty] | X | needs further investigation and data collection
|  |  | AI-powered Screening Tools that can provide immediate risk assessments | X | [7 empty] | X | May be regulatory questions around AI in regards to criminal justice. Needs further investigation.
|  |  | Continue Green Labs testing to better understand the effects of cannabis impairment. | X | [5 empty] | X |  |  | already being done
|  | Prohibit open alcohol containers in passenger vehicles. | Continued support for legislation of Open Container Law: Support CTDOT’s legislative proposals (such as 2020 Bill 151), prohibiting open alcohol containers in motor vehicles. | X |  |  | X (CR) |  | X |  |  | X | can continue to support, but needs legislative support to pass
|  |  | Publicize high fines | X | [6 empty] | X |  | needs further development for public awareness campaign
|  |  | Vehicle confiscation (temporary) | X | [6 empty] | X |  | needs further development
|  |  | License points added to a drivers record for open container violations and repeat offenders | X | [7 empty] | X | needs further investigation and policy development
|  | Driving school requirements; have to have education specific to cannabis in conjunction with alcohol impairment. | Program for adults to increase impaired driving awareness related to drug use and cannabis. | X |  |  |  |  | X |  | X |  | needs further development
|  |  | Program for adults as well to spread awareness. | X | [6 empty] | X |  | needs further development for more widespread implementation
|  |  | Include cannabis and drug use specific questions in driving school exams | X | [6 empty] | X |  | needs further development
| Improve public information and strengthen enforcement against impaired driving. | Set sanctions for high blood alcohol content (BAC) officers and for first time high BAC offenders. | Swift justice programs used to fast track court procedures for high BAC cases. | X | [7 empty] | X | needs time to develop and implement
|  |  | Mobile apps that provide information on penalties for high BAC levels. | X | [7 empty] | X | needs further development
|  | Educate, communicate, publicize, and enforce zero tolerance laws. | Increase education with law changes. | X | [6 empty] | X |  | needs further development
|  |  | Look at impact of impaired driving in different communities across Connecticut. | X | [7 empty] | X | long term study needs further development
|  |  | CT DOT, CT DPH, & local health depts. To conduct public awareness campaigns on dangers of operating motor vehicles under the influence of drugs and cannabis. |  |  | X (Sec. 8) |  |  |  |  | X |  | already supported through vision zero, but needs time to develop campaigns
|  |  | Highlight the importance of sober driving during the month of December during Office of National Drug Control Policy’s National Drunk and Drugged Driving Prevention month and NHTSA’s "Drive Sober or Get Pulled Over" mobilization. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  | X | X |  |  | Already being done. Continue to help spread the word.
|  |  | Safe States DUI Media Campaign |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Healthcare Heroes Impaired Driving: A hospital-based impaired driving messaging approach to behavior change |  | X |  |  |  |  | X |  |  | continue to support; need to investigate for more widespread use
|  |  | Mothers Against Drunk Driving (MADD) Initiatives |  | X |  |  |  |  | X |  |  | continue to support
|  |  | High visibility billboards to advertise zero tolerance policy | X | [6 empty] | X |  | needs time to develop and implement
|  |  | Impaired driving administration |  | X |  |  |  |  | X |  |  | continue to support
|  | Increase the number of officers trained and expand the Standardized Field Sobriety Testing program focusing on local law enforcement. | Cooperate with the SHSP goal to increase the number of certified standardized field sobriety test practitioners and instructors. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  | X |  |  | consider funding for further development
|  |  | Collaborate with other municipal police departments that have had successes in reducing substance-impaired driving crashes |  |  |  | X (CR, METRO) |  |  |  | X |  | needs further investigation
|  |  | Standardized Field Sobriety Training (SFST) |  | X | [5 empty] | X |  | continue to support
|  |  | E-learning modules offering Field Sobriety Testing training | X | [6 empty] | X |  | needs further investigation
|  | Reduce BAC limit from 0.08 to 0.05. | Continued push for legislation to reduce BAC from 0.08 to 0.05. | X |  |  |  |  | X | X |  |  | continued support is near-term; actual legislation change is long-term
|  |  | Amend local bylaws to reduce BAC limit | X | [7 empty] | X | needs time to develop policies and obtain support
|  | Increase the number of officers certified Drug Recognition Experts (DREs). | Support Phlebotomy & DRE training for officers. | X |  |  |  |  | X | X |  |  | Pilot law enforcement phlebotomy program taking place. Continue Drug Recognition Expert (DRE) training for officers.
|  |  | Augment regional and local support of officers to get certified as DREs |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | continued support for program
|  |  | DRE Overtime Call Out Instructor support |  | X |  |  |  |  | X |  |  | already being done
|  |  | Drug Evaluation and Classification Program(DECP) |  | X |  |  |  |  | X |  |  | already being done
|  |  | DRE Exchange Programs | X | [6 empty] | X |  | needs time to investigate
|  |  | Special grant programs for departments that want to increase their number of DRE officers | X | [6 empty] | X |  | determine ways to increase funding to train officers
|  | Expand officers trained in Advanced Roadside Impaired Driving Enforcement (ARIDE). | Augment regional and local support of officers to take the ARIDE program |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | MPO support
|  |  | Ignition Interlock device (IID) Staff Positions |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Have ARIDE-trained officers conduct community workshops to explain their work and foster public cooperation. | X |  |  |  |  | X |  | X |  | needs further development and support.
| Focusing on prosecution and imposing sanctions through implementation or enhancement. | Increase law enforcement recognition and conviction of impairment (beyond alcohol) | Support legislation of E-warrant use with roadside drug impairment testing. | X |  |  |  |  | X |  | X |  | Pilot e-warrant program taking place; will need time for development for full deployment
|  |  | Increase high visibility enforcement. | X |  |  |  |  | X |  | X |  | need more staff to implement and use all available funding
|  |  | Support efforts to digitalize and create a central, electronic database for A-44 forms. | X |  |  |  |  | X |  | X |  | efforts are underway
|  |  | Segregate ticketing for alcohol and cannabis to allow for improved trend evaluation. | X | [7 empty] | X | needs further development
|  |  | Conduct regional high-visibility impaired driving enforcement program. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER) |  |  |  | X |  | needs further development
|  |  | DUI Overtime Enforcement and Equipment: Add additional saturation patrols and checkpoints during holiday crackdowns and weekends. |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Inter-Agency Expert Teams: specialized units comprised of experts in pharmacology and law to assist in complex cases involving other substances. | X | [7 empty] | X | needs further investigation
|  |  | Increase DUI checkpoints, especially during time periods with historically high impaired driving crashes |  |  |  |  | X |  |  | X |  | may need more data analysis and more staff needed to implement
|  | Increase prosecution and conviction of DUI offenders | Continue to enforce the interlock devices for all Connecticut DUI/ DWI/OUI first time offenders. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | continue to support
|  |  | Traffic Safety Resource Prosecutor (TSRP): One Statewide TSRP position will be funded in order to assist in successfully prosecuting DUI and other drug/impaired related cases through training/education programs. |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Forensic audit teams: Establish specialized teams to scrutinize the details of DUI cases for gaps or loopholes that offenders might exploit. | X | [6 empty] | X |  | needs further development
|  |  | Virtual courtroom simulators: Create training simulators for prosecutors to practice DUI cases. | X | [7 empty] | X | needs further development
|  | Assess administration of licensing sanctions | Administrative per se Hearing Attorney(s): funding for two attorneys. |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Third-Party Audits: Hire external agencies to audit the effectiveness and fairness of licensing sanctions. | X | [6 empty] | X |  | needs further development
|  |  | Machine Learning Forecasting: Use predictive analytics to model the potential long-term effects of various sanction policies. | X | [7 empty] | X | needs further investigation and development
|  | Implement DUI offender license plate sanctions | Public Awareness Campaign: Use media channels to inform the public about the meaning of the specialized license plates. | [8 empty] | X | needs further development
|  | High-supervision Driving While Intoxicated (DWI) Courts | In SHSP. | [8 empty] | X | needs further development
|  | Remove option for refusal of BAC test | Sanction ladder: Develop a tiered system of increasing penalties for those who refuse BAC testing, from fines to vehicle impoundment. | X | [7 empty] | X | needs further development and legislation
|  |  | Consent education: Create educational campaigns that inform drivers they consent to BAC tests as a condition of receiving a driver's license. | X | [7 empty] | X | needs further development
|  | Educate officers and courts to identify re-offense and felony charge | Judicial Training Modules: Provide specialized training for judges and prosecutors focused on identifying and prosecuting repeat DUI offenders. | X | [6 empty] | X |  | needs further development
HOW?
HOW?
WHEN?

## AGGRESSIVE DRIVER
BEHAVIORAL EA: AGGRESSIVE DRIVING
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Aggressive Driver Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSP 21-23 | Vision Zero | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of aggressive driving fatalities and serious injuries to less than 502 by 2026. | Increased speed detection and law enforcement. | Strengthen speed detection measures. | Regional and municipal support for high-visibility enforcement campaigns that specifically target speed and aggressive driving |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  | X |  |  | support can be encouraged at anytime; actually increasing high visibility enforcement has staffing challenges
|  |  | Integrate the speed management countermeasures into roadway departure, intersection, and pedestrian safety areas. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | speed management overlaps with all EAs
|  |  | Speed Radar Upgrades | X | [6 empty] | X |  | needs further investigation
|  |  | Drone Surveillance: Utilize drones for aerial speed detection in problem areas. | X | [6 empty] | X |  | needs further investigation
|  |  | Training Programs offering specialized training for officers regarding speed detection devices use. | X | [6 empty] | X |  | needs further investigation
|  |  | Work to receive dedicated speed funding from NHTSA. | X | [6 empty] | X |  | may take time to receive
|  | Explore automated enforcement. | Implementation of automated enforcement. | X |  |  |  |  | X | X |  |  | Work zone automated enforcement pilot complete; just passed legislation to allow for permanent program Implementing speed cameras and red-light running cameras: School zones, pedestrian safety zones, and work zones are key locations for automated enforcement.
|  |  | Regional collaboration and resource sharing of scientifically valid speed measurement technology for enforcement. |  |  |  | X (CR, SC) |  |  |  | X |  | needs further development
|  |  | Any municipality may authorize the use of automated traffic enforcement safety devices at locations within school zones, pedestrian safety zones and other places as approved by CT DOT. |  |  | X (Sec. 11) |  |  |  | X |  |  | already in place
|  |  | More Pilot Programs | X | [6 empty] | X |  | needs further investigation
|  |  | Public Awareness campaigns on implementation of automated enforcement | X | [6 empty] | X |  | needs further development
|  |  | Automated enforcement usage in Work Zones - Pilot Study | X | [5 empty] | X |  |  | permanent program through legislation and under development
|  | Install red-light running cameras. | Intersection Analysis: Use data to identify the most dangerous intersections for red-light running | X | [5 empty] | X |  |  | legislation passed; municipalities are lead to do this
|  | Install confirmation lights. | Traffic Flow Studies to determine where confirmation lights would be most effective. | X | [7 empty] | X | needs further investigation
|  | Analyze data to identify contributing factors. | 1906 Racial Profiling: Develop a new standardized method to efficiently and effectively collect racial profiling data from traffic stops |  | X | [5 empty] | X |  | needs time to develop
|  | Use high-visibility enforcement. | Increase high visibility enforcement COG support: Regional and municipal support for high-visibility enforcement campaigns that specifically target speed and aggressive driving | X | X |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) | X | X |  | X |  | Increasing staffing is one of the main challenges to increasing enforcement presence on CT roadways. Looking to increase at both the state and local levels.
|  |  | FHWA funding towards HVE equipment, training, enforcement, and salaries. | X | [6 empty] | X |  | need to determine how
|  |  | Speed and Aggressive Driving Enforcement focusing on contributing factors indicated in the problem identification write up for PTS. |  | X | [5 empty] | X |  | needs time for further development
|  | Additional Strategies not in SHSP | Integration of GPS notifications for drivers showing “Speed limit vs. your speed” and “Speed trap ahead” |  |  |  |  | X |  |  |  | X | support car manufacturers
|  |  | Explore speed limitation and ignition interlock device (IID) installation in cars for repeat offenders and regular drivers |  |  |  |  | X |  |  |  | X | needs legislation
| Identifying additional law enforcement resources aimed towards reducing speed related fatalities and serious injuries. | Purchase, deploy, and utilize speed measuring devices. | Deploy speed measuring devices. | X | [7 empty] | X | Variable Speed Limit on Interstates may be beneficial. Explore speed limiter usage like ignition interlocks.
|  |  | Explore the possibility of creating safety corridors where a segment of roadway has a higher-than-expected number of fatal and/or serious injury crashes due to driver behaviors. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | needs further investigation
|  |  | Budget allocation: Secure budget approval for the purchase of state-of-the-art speed measuring devices like laser speed guns, radar devices, and speed cameras. | X | [6 empty] | X |  | need to determine funding source(s)
|  |  | Deployment Strategy: Use crash and speeding data to identify hotspots where speed measuring devices will be most effectively deployed. | X | [6 empty] | X |  | need more data collection
|  | Use law enforcement liaisons to link partners. | Coordinate with local agencies, local police and fire departments, the auto insurance industry, and CTDMV to disseminate and educate the public on the hazards of aggressive driving. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | needs time to develop coordination
|  |  | Identify Key Partners: Determine which organizations (e.g., local government, community organizations, schools, and hospitals) would be valuable partners in reducing aggressive driving. - In SHSP | [7 empty] | X |  | needs time to develop
|  | Repeat speed offenders. | Nevada doing study on repeat speed offenders. Keep in mind for future reference. | X | [6 empty] | X |  | use as reference
|  |  | Create a database to track repeat speed offenders. | X | [6 empty] | X |  | needs data collection
|  |  | Tiered penalties for repeat speed offenders. | X | [7 empty] | X | would need legislation
|  |  | Vehicle restrictions such as speed ignition interlocks for repeat offenders. | X | [7 empty] | X | would need legislation
| Use judicial and legislative strategies to reduce speeding related fatalities and serious injuries. | Support legislation to strengthen penalties | Support legislation to strengthen penalties. | X |  |  |  |  | X |  |  | X | Focus on addressing repeat offenders.
|  |  | Conduct comprehensive studies to determine what kinds of legislative changes would most effectively deter speeding. | X | [6 empty] | X |  | needs data collection and further investigation
|  |  | Partner with public safety advocacy groups to lobby for legislation that strengthens penalties for speeding. | X | [6 empty] | X |  | investigate ways to support
|  |  | Provide expert testimony during legislative sessions to support the passing of new laws. | X | [6 empty] | X |  | need to determine how to support this
|  | Strengthen adjudication of speed citations. | Increase adjudication of citations. | X |  |  |  |  | X |  |  |  | Focus on addressing repeat offenders. Emphasis on supporting more adjudication of citations as opposed to increasing fines.
|  |  | Create special court dockets focused solely on speeding and other traffic offenses to expedite cases and provide more consistent adjudication. | X | [7 empty] | X | needs time to investigate and implement
|  |  | Develop a set of guidelines for the judiciary outlining recommended penalties based on the severity of the speeding offense and other contributing factors. | X | [7 empty] | X | needs time to develop
|  | Graduated drivers license for repeat offenders. | Require an aggressive driving or speed awareness course as a prerequisite for moving through the graduated licensing tiers. | X | [7 empty] | X | needs time to develop
|  |  | Establish criteria for the removal of restrictions and the reinstatement of a full license, based on a sustained period of safe driving behavior. | X | [7 empty] | X | needs time to develop
| Incorporate infrastructure treatments to reduce aggressive driving and speeding behavior. | Employ traffic calming strategies. | Include the installation of the Intelligrants IGX E-grants management system software and maintenance |  | X | [5 empty] | X |  | continue to support
|  |  | Install speed bumps/humps, chicanes, roundabouts, pedestrian crossings, and/or road diets | X |  |  |  |  | X | X | X | X | various time frames to implement depending on strategy
|  | Prepare complete streets policies and implementation projects. | Complete streets policy implementation. | X | [5 empty] | X |  |  | Support CTDOTs complete streets policy with focus on implementing traffic calming and speed management strategies into projects.
|  |  | Involve local communities, transport agencies, and other stakeholders in the planning and implementation process. | X | [5 empty] | X |  |  | continue to spread the word about the CTDOT complete street policy
| Improve understanding and awareness of the impacts of speed and crash outcomes. | Provide additional education and public information to better understand the consequences of speeding and aggressive driving, especially in marginalized communities and areas with an overrepresentation of speed related severe crashes. | Coordinate with local agencies, local police and fire departments, the auto insurance industry, and CTDMV to disseminate and educate the public on the hazards of aggressive driving. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | support to various safety stakeholders
|  |  | Speed and Aggressive Driving High Visibility Enforcement Media Buy |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Connecticut Police Chiefs Association-Public Information and Education-New Planned Activity (Breaking Barriers) |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Grassroots Campaigns(Community Workshops, Local Ambassadors, Door-to-Door Campaign) | X | [6 empty] | X |  | support; and need time to get more support
|  |  | Police Traffic Services Program Administration providing further law enforcement education |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Social media campaigns highlighting insurance cost implications of speeding tickets. | X | [6 empty] | X |  | needs time to develop
|  |  | Use of media campaigns to show consequences and target overly aggressive drivers |  |  |  |  | X |  |  | X |  | needs time to develop
Note on K46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend implementation Reply: Added as recommendation for implementation.
HOW?
HOW?
WHEN?

## UNRESTRAINED OCCUPANTS
BEHAVIORAL EA: UNRESTRAINED OCCUPANTS
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Unrestrained Occupant Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSP 21-23 | Vision Zero | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of unrestrained occupant fatalities and serious injuries to less than 230 by 2026. | Increasing communication measures and educational campaigns. | Child passenger safety events in underserved communities. | Support and increase funding and education for car seat distribution and use geared towards increasing Child Passenger Safety (CPS). | X |  |  |  |  | X | X |  |  | continue to support program and look for ways to increase funding
|  |  | CT DOT, Dept. of Education, DMV, DPH, social services, and veteran affairs to establish a program promoting use of seat belts among vulnerable communities. |  |  | X (Sec. 15) |  |  | X |  | X
|  |  | Waterbury Area Traffic Safety Program |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Hangtime Community Traffic Safety Program |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Western Connecticut Child Passenger Safety Support |  | X |  |  |  |  | X |  |  | continue to support
|  | Communicate child restraint system through outreach and campaigns. | Coordinate with AAA, CTDOT and T2 Center to explore potential educational/ outreach efforts promoting seat belt use |  |  |  | X (CR, NV) |  |  |  | X |  | need time to coordinate and develop more educational materials
|  |  | Communicate the new child safety seat laws coordinating with multiple agencies like Safe Kids CT, local police and fire departments, the YMCA |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | already being done - need to consider additional ways to reach more people
|  |  | Coordinate with private sector to host car seat clinics and publicize the safe fitting stations in the region using earned media outlets. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  | X |  |  | need to develop program
|  |  | Child Passenger Safety Support-Training |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Child Passenger Safety Support-Fitting Stations |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Targeting Disparities to Increase Proper Car Seat Use |  | X | [5 empty] | X |  | New planned activity
|  |  | Safe Kids Hartford Child Passenger Safety Program |  | X | [5 empty] | X |  | New planned activity
|  |  | Yale New Haven Children's Hospital Community Traffic Safety Program |  | X |  |  |  |  | X |  |  | already in place
|  |  | Look Before you Lock, Where's Baby |  | X |  |  |  |  | X |  |  | continue to support
|  | Social norming campaigns. | Continue the Click it or Ticket enforcement campaign. | X |  |  | X (CR, SC) |  |  | X |  |  | continue to support
|  |  | Occupant Protection Media Buy and Earned Media |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Tie insurance rates to education and driver behavior to support wearing a seatbelt |  |  |  |  | X |  |  | X |  | need time to reach out to insurance companies
|  |  | Use of awareness & social media campaigns promoting seat belt use |  |  |  |  | X |  |  | X |  | needs time to develop
|  | "Saved by the Belt" campaigns. | Occupant Protection Program Administration |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Safety Belt Convincer/Rollover Simulator Education and Equipment |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Occupant Protection Public Information and Education |  | X |  |  |  |  | X |  |  | continue to support
| Strengthening laws and enforcement | Primary enforcement for rear seated passengers | Support primary enforcement law for rear seated passengers. | X |  |  |  |  | X |  |  | X | Currently a secondary enforcement law.
|  | High-visibility, highly publicized, focused enforcement | Increase and promote high visibility enforcement. | X |  |  |  |  | X | X |  |  | staffing one of main challenges to be able to increase HVE
|  |  | Increase enforcement resources and staffing. | X | [6 empty] | X |  | needs time to determine how to increase staffing and resources
|  |  | Coordinate with NHTSA’s calendar of high-visibility enforcement of safety belts and child safety enforcement |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | needs time to develop local programs
|  | Seatbelt enforcement checkpoints | Continue regional and municipal enforcement using checkpoints, roving, and saturation patrols. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  | X |  |  | continue to support programs
|  |  | Continue municipal enforcement providing car seat fitting. |  |  |  | X (METRO) |  |  | X |  |  | continue to support programs
|  |  | Targeted enforcement for younger drivers to influence behavior while considering equity |  |  |  |  | X |  |  | X |  | needs time to develop program
|  | Before and after seat belt observation surveys | In SHSP. | [8 empty] | X | needs time for data collection
|  | Coordinated nighttime belt enforcement with other offenses | In SHSP. | [6 empty] | X |  |  | continue to support
|  | Additional Strategies not in SHSP | Strengthen legislation and enforcement for repeat offenders. | X |  |  |  |  | X |  |  | X | needs time to gather data and develop policies and legislation
|  |  | Consider requiring additional trainings for repeat offenders. | X |  |  |  |  | X |  |  | X | needs time to develop
|  |  | Increase Child Passenger Safety techs in police departments |  |  |  |  | X |  |  | X |  | needs time to hire and determine funding
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend implementation, since it was required by Vision Zero law Reply: Added as recommendation for implementation.
Note on K27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This would be a significant lift - we can support it but I'd probably make it a long-term priority Reply: Updated to long-term.
Note on M13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: recommend moving to near-term - this is already happening Reply: Added to near-term.
HOW?
HOW?
WHEN?

## MOTORCYCLE
BEHAVIORAL EA: MOTORCYCLE
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Motorcycle Crashes | Activity/Initiative Source |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSP 21-23 | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of motorcycle fatalities and serious injuries to less than 293 by 2026 | Strengthen awareness and education efforts. | Conduct targeted media to promote helmet use | Increase media outreach and encourage motorcycle riders to wear protective clothing and gear. |  |  | X (METRO) |  |  |  | X |  | needs time to develop more outreach
|  | Conduct targeted media to inform riders of dangers of impaired riding | Coordinate with local dealerships and public and private sector agencies to promote safety campaigns, encourage older riders to wear helmets, goggles, protective clothing and gear, and encourage motorists to share the road. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | needs time to coordinate
|  |  | Support the None for The Road campaign and www.rider4ever.com, encouraging riders to not drink and ride and to ride safely. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  | X |  |  | continue to support
|  | Maintain and promote websites aimed at changing unsafe riding behavior, such as www.ride4ever.com | Promote various motorcycle safety awareness resources, such as Helmetcheck.org, the Motorcycle Safety Foundation, Interactive Scenic Ride Map, and CT Travel Smart websites |  |  | X (CR, METRO, NH, NV, RIVER, SC) |  |  | X |  |  | continue to support; need time increase promotion/outreach
|  | Promote awareness of high-visibility clothing | Increase media outreach and encourage motorcycle riders to wear protective clothing and gear. |  |  | X (METRO) |  |  |  | X |  | needs time to develop more outreach
|  |  | Promote high visibility clothing use for riders. |  |  |  | X |  |  | X |  | needs time to develop more outreach
|  | Strengthen social norms around helmet use | Require mandatory safety classes for riders that emphasize helmet use. |  |  |  | X |  | X |  |  | continue to support
|  | Expand upon and Campaign the CT Rider Education Program | Continue support for CT Rider Education Program to be mandatory for all riders. | X |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  | X | X |  |  | continue to support
|  |  | Motorcycle Safety Program Administration |  | X |  |  |  | X |  |  | continue to support
|  |  | HSO Staff Community Outreach: Disseminate HSO messages to the public by public outreach and education |  | X |  |  |  | X |  |  | continue to support
|  | Encourage riders to obtain motorcycle endorsement | Continue to support the insurance industry’s rate discount for CONREP graduates. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) | X |  | X |  |  | continue to support
|  | Campaigns about sharing the road with motorcycles | Provide targeted education and implementation of campaigns on sharing the road with motorcycles. | X | X |  |  | X | X |  |  | Continue to support Media campaigns such as “Watch for motorcycles” especially during Spring when more riders are on the roads
| Improve visibility through highly visible and protective wear. | Enact universal helmet law | Continue to support legislation of a helmet law in CT. | X |  |  |  | X |  |  | X | Continue to support
|  |  | Require newly licensed motorcycle users must wear a helmet for first 2 years of riding (currently a law in Delaware). | X | [6 empty] | X | Hard to enforce; 2024 introduced in legislation but didn't make it through
|  |  | Riders under 18 must wear a helmet. | X | [6 empty] | X | Needs legislation
|  | Promote Snell-certified helmets | Coordinate with local dealerships and public and private sector agencies to promote safety campaigns, encourage older riders to wear helmets, goggles, protective clothing and gear, and encourage motorists to share the road. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | some campaigns need time to develop
| Increased data analysis, prioritization, and enforcement. | Conduct nighttime high-visibility enforcement along with improved messaging and communication | In SHSP. | [6 empty] | X |  | some programs in place; some need further development
|  | Expand vehicle impoundment for substance-impaired and high speed riders | In SHSP. | [6 empty] | X |  | needs time for further development
|  | Analyze data to identify locations and times for impairment and speed enforcement | In SHSP. | [7 empty] | X | needs time for data collection and analysis
| Additional strategies not part of SHSP |  | Integrating infrastructure improvements such as median barriers |  |  |  | X |  |  |  | X | needs time to develop further for potential installation
HOW?
HOW?
WHEN?

## DISTRACTED DRIVING
BEHAVIORAL EA: DISTRACTED DRIVING
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Distracted Driving Crashes | Activity/Initiative Source |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSP 21 - 23 | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of distracted driving fatalities and serious injuries to less than 93 by 2026. | Enforcement and education strategies should be considered. | Increase enforcement, especially conduct high-visibility distracted driving enforcement campaigns. | Increase high visibility enforcement. | X |  |  |  | X | X |  |  | Increasing staffing is one of the main challenges to increasing enforcement presence on CT roadways. Looking to increase at both the state and local levels.
|  |  | Regionally conduct high-visibility distracted-related enforcement, focusing on towns with higher rates of distracted driving related fatalities and injuries. |  |  | X (CR, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | needs time to collect data
|  |  | In addition to high visibility enforcement, use unmarked patrol vehicles and spotter techniques in high traffic areas. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | similar challenges as HVE
|  |  | Conduct high-visibility distracted-related enforcement - U Drive. U Text. U Pay. This is done each April in partnership with NHTSA. |  | X | X (METRO) |  |  | X |  |  | continue to support
|  |  | HVE distracted driving-enforcement using data sourced from table DD-6 to prioritize funding. |  | X |  |  |  | X |  |  | continue to support
|  | Educate the driving public through media campaigns, public info champaigns, and education programs. | Continue awareness campaigns for distracted driving. | X |  |  |  | X |  | X |  | Promoting awareness around phone silencing tips (i.e. automatic message when driving) & vehicle technology tips. Partnering with employers to promote safe driving.
|  |  | Increase regional public outreach of distracted driving that reach specific segments of the targeted audience. Coordinate with NHTSA’s calendar of outreach. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | needs time to collect data
|  |  | Coordinate distracted driver messages with multiple agencies: DMV, DOT, and DESSP. |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC) |  |  |  | X |  | needs time to coordinate
|  |  | Distracted Driving Public Messaging Campaign |  | X |  |  |  | X |  |  | continue to support
|  |  | Distracted Driving Public Information and Education |  | X |  |  |  | X |  |  | continue to support
|  |  | Distracted Driving Education Programming and Younger Driver Education |  | X |  |  |  | X |  |  | continue to support
|  | Outreach programs addressing social norms. | Organize community art projects that create public installations highlighting the importance of focused driving. | X | [5 empty] | X |  | needs time to develop further
|  | Incorporate family safe driving agreement in driver education classes. | Introduce a certification program for schools and educators that emphasizes the integration of family safe driving agreements into driver education. | X | [5 empty] | X |  | needs time to develop further
| Partnerships and technology strategies may support the reduction of fatalities and severe injuries. | Partner with employers. | Municipalities can use AAA’s free Distracted Driving Public Service Announcement to raise awareness by contacting the AAA Manager of Public and Government Affairs. |  |  | X (CR) |  |  | X |  |  | continue to support
|  |  | Work with insurance companies to provide policy discounts for staying focused. |  |  |  | X |  |  | X |  | needs time to develop further
|  | Promote use of smartphone technology to limit or eliminate calls or texting while driving. | Collaborate with major employers to implement incentivized safe driving programs for their employees. Employees who demonstrate safe driving habits could receive benefits or rewards. | X | [5 empty] | X |  | needs time to determine to collaborate further
|  |  | Create a "Safe Driving Mode" app that offers a variety of rewards, such as discounts on insurance premiums. | X | [6 empty] | X | needs time to investigate further
|  |  | Develop augmented reality glasses or heads-up displays that provide information without requiring drivers to look at their phones. | X | [6 empty] | X | needs time to investigate further
|  |  | Explore data sharing to identify when drivers are operating vehicles while on their phones. |  |  |  | X |  |  |  | X | needs time to investigate further
|  |  | Create cell phone “lock down” area. |  |  |  | X |  |  |  | X | needs time to investigate further
|  |  | Encourage setting phone default to “do not disturb” message when driving. |  |  |  | X | X |  | X |  | needs time to develop outreach
|  | Promote understanding or vehicle technology. | Use of BURLA system to see interactions with mobile phones at the time of crashes. | X | [6 empty] | X | Needs to be done by someone who is BURLA certified. Expensive system.
|  |  | Upgrade to the Electronic Citation Processing System e-Citation Version 2, which can reduce data input errors; improve police officer efficiency. |  |  | X (CR, SC) |  |  |  | X |  | needs time to develop further
|  |  | Collaborate with automotive manufacturers to offer free or discounted training sessions where drivers can learn about their vehicle's technology and how it enhances safety. | X | [5 empty] | X |  | needs time to investigate further
Note on J26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend implementation Reply: Added as recommendation for implementation.
HOW?
HOW?
WHEN?

## x2 (hidden)
STRATEGY 4: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x3 (hidden)
STRATEGY 6: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x4 (hidden)
STRATEGY 9: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x5 (hidden)
STRATEGY 10: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x6 (hidden)
STRATEGY 11: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?