## ROADWAY DEPARTURE
INFRASTRUCTURE EA: ROADWAY DEPARTURE
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Roadway Departure Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSIP 21 -24 Implementation Plans | Vision Zero | RTSP (COGS) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of roadway departure fatalities and serious injuries to less than 665 by 2026. | Keep vehicles from encroaching on the roadside along tangents. | Provide enhanced edge line markings. | Increase 6" edgeline implementation/installation | X |  |  |  |  | X |  | X |  | Being installed on state roads through vendor-in-place (VIP) resurfacing in rural town centers for edgelines and centerlines; and some municipalities are installing on their roads; will need time for policy changes if to implement statewide
|  |  | Support implementation/installation of wet reflective pavement markings | X |  |  |  |  | X | X |  |  | Already typically used on new pavement (not chip seals) Short sections in smaller reconstruction projects installed case by case
|  |  | Install horizontal curve pavement marking treatments; pavement marking study on municipal roads | X | X |  |  |  | X |  | X |  | Needs further investigation especially with results from municipal pavement marking study
|  |  | Implement proven systemic safety countermeasures: pavement markings on curves. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  | X |  |  | Various countermeasures
|  |  | Introduce painted left-turn channelization | X | [7 empty] | X | needs further investigation
|  |  | Introduce raised/curb left turn channelization | X | [7 empty] | X | needs further investigation
|  |  | Install in-road reflectors along centerlines and/or edgelines of curves |  |  |  |  | X |  |  |  | X | challenge with maintenance in CT due to winter weather
|  |  | Install zigzagged pavement markings at curves |  |  |  |  | X |  |  |  | X | needs further investigation and data to determine where appropriate
|  |  | Install speed reduction markings on approaches to curves and stops |  |  |  |  | X |  | X |  |  | already installed in some locations; need to study further to determine effectiveness
|  | Install shoulder rumble strips and widen shoulders. | Implement proven systemic safety countermeasures: center line and edge line rumble strips. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  | X | X |  | CLRs already being installed; need to investigate edgeline rumble strips further
|  |  | Install rumble strips along horizontal curvature based on crash data at specific locations. |  |  |  | X (METRO) |  |  |  |  | X | need to investigate further
|  |  | Install transverse rumble strips as a traffic calming device. | X | [7 empty] | X | need to investigate further for appropriate locations; challenge is noise to nearby residences
|  |  | Implement in-lane and shoulder rumble strips. |  |  |  |  | X |  | X |  |  | shoulder rumble strips installed on limited access highways already
|  | Eliminate edge drop-offs. | In SHSP. | [8 empty] | X | Needs further investigation - see safety edge too
|  | Provide a safety edge. | Utilize state guiderail inventory for crash data analysis; guiderail study | X | X |  |  |  | X |  | X |  | Share information with municipalities to assist with guiderail upgrades.
|  |  | Implement proven systemic safety countermeasures: safety edge implementation. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  |  | X |  | needs further investigation
| Keep vehicles from encroaching on the roadside at curves. | Install advanced signing. | Install horizontal curve signing on state roads |  | X |  |  |  |  | X |  |  | projects completed
|  |  | Install horizontal curve signing on municipal roads. |  | X |  |  |  |  | X |  |  | projects in design and construction
|  |  | Tag utility poles with retroreflective placards. | X | [5 empty] | X |  |  | some utility companies do this when installing new poles
|  |  | Implement proven systemic safety countermeasures: improved signage |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  | X |  |  | need time to investigate systemic installations
|  |  | Install advanced static curve warning signs. | X | [5 empty] | X |  |  | performed in conjunction with horizontal curve warning sign projects
|  |  | Install combination horizontal alignment/advisory speed signs. | X | [5 empty] | X |  |  | performed in conjunction with horizontal curve warning sign projects; advisory speed signs only where appropriate and as allowed in MUTCD.
|  |  | Install a combo of chevron signs, curve warning signs, and/or sequential flashing beacons | X | [6 empty] | X |  | some work completed, some underway, some needs further investigation
|  |  | Install warning signs and/or pavement markings on roadways sections with steep grades (over 5%) |  |  |  |  | X |  |  |  | X | needs further investigation and data collection
|  | Install chevrons. | Install chevron signs on horizontal curves. | X | [5 empty] | X |  |  | state road curves completed; municipal designs underway
|  |  | Install oversized chevron signs. | X | [6 empty] | X |  | need to investigate if and where this would be appropriate
|  |  | Use of illuminated sequential chevrons on sharp curves. |  |  |  |  | X |  |  |  | X | need to investigate if and where this would be appropriate; maintenance challenges
|  | Provide high-friction surface treatment. | Continue installing HFST. | X | X |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  | X | X |  |  | continue to support; challenge with funding due to high cost of treatment
|  |  | Increase pavement friction. | X | [5 empty] | X |  |  | other than HFST this could include micromilling and has been done in some curves
|  | Improve geometry such as changing superelevation, or widening the radius. | Incorporate the use of proven technology and roadway designs that make roadways safer |  |  |  | X (NHC) |  |  |  |  | X | needs further investigation and data collection
|  |  | Ensure sightlines and clear zones are maintained |  |  |  |  | X |  | X |  |  | can be done at anytime; challenge of where/when to investigate
|  | Educate public on safety treatment effectiveness. | UCONN T2 center offering roadway departure countermeasure training through FHWA. | X | [5 empty] | X |  |  | support training
|  |  | Conduct high-visibility local enforcement, media campaigns and public outreach on identified corridors with a high number of severe roadway departure crashes |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  | X |  | needs further investigation and development
|  | Provide adequate lighting. | Provide increased highway lighting. | X | [7 empty] | X | needs further investigation of additional appropriate locations
|  |  | Increase illumination at curves. |  |  |  |  | X |  |  |  | X | needs further investigation; challenge with who will install, own, and maintain
| Keep vehicles on the road via speed management. | Provide speed management pavement markings. | Install in-lane curve warning pavement markings. | X | [5 empty] | X |  |  | speed reduction markings have been installed at several locations; need to study their effectiveness
|  | Install speed feedback signs. | Continued use of speed feedback signs. | X |  |  |  |  | X | X |  |  | Speed feedback signs provided to all town and tribal owned roadways that requested them through the T2 center. Data analysis to follow on effectiveness.
|  | Update speed limit setting policy. | Design guidance target speeds being developed by CT DOT. | X | [6 empty] | X |  | 85th percentile speeds have been the previous standard but we do not want to keep designing roadways in anticipation of people going faster. Guidance being developed
|  | Provide education to users on safe speeds. | T2 Center offering roadway departure countermeasure training through FHWA. | X | [5 empty] | X |  |  | support training
| Minimizing the likelihood of crashing into an object or overturning vehicles. | Provide safer slopes. | In SHSP. | [8 empty] | X | needs further investigation; see safety edge
|  | Increase clear zone widths. | Remove or relocate roadside fixed objects out of clear zone. | X | [5 empty] | X | X | X | continue to support in projects during design
|  | Improve barriers. | Design the roadside to include roadside barrier systems (guiderail, impact attenuators, and end treatments) or manage roadside vegetation, trees, and other fixed objects, to maintain a clear zone, in order to minimize the severity of crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  |  | X |  | consider use of guiderail inventory while investigating this further
| Reducing head-on crashes. | Install centerline rumble strips (CLRS). | Continued installation of CLRS; Install centerline rumble strips as part of VIP & annual resurfacing projects. | X | X |  |  |  | X | X |  |  | ongoing program in place when roads are resurfaced
|  |  | Centerline rumble strip screening and outreach. |  | X |  |  |  |  | X |  |  | study underway
|  |  | Implement proven systemic safety countermeasures: center line and edge line rumble strips. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST, SCR) |  |  | X |  |  | already being installed; need to investigate further appropriate locations to consider edgeline rumble strips
|  |  | Install rumble strips along horizontal curvature based on crash data at specific locations. |  |  |  | X (METRO, NHC) |  |  |  |  | X | need to investigate where feasible
|  | Install center buffers. | In SHSP. | [8 empty] | X | needs further investigation
|  | Install median buffers. | In SHSP. | [8 empty] | X | needs further investigation
| Comprehensive effective strategies for mitigating roadway departure crashes. | Provide safety corridors with enforcement. | Support implementation of automated enforcement infrastructure to address speeding. | X |  |  |  |  | X | X |  |  | legislation passed; program in place; municipalities working on implementation
|  |  | Increasing enforcement and utilization of enforcement grants. | X |  |  |  |  | X |  | X |  | challenge of adequate staffing to conduct; grant $ available
|  |  | Use of high visibility enforcement. | X |  |  |  |  | X |  | X |  | challenge of adequate staffing to conduct
|  |  | Municipalities can identify and implement spot location-based safety countermeasures on Connecticut’s State, local, and tribal roads. |  |  |  | X (METRO, NHC) |  |  | X | X | X | needs further investigation for appropriate locations
|  |  | Conduct high-visibility local enforcement, media campaigns and public outreach on identified corridors with a high number of severe roadway departure crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  | X |  | similar enforcement challenges related to staffing
|  | Conduct RSAs (roadside safety audits). | In SHSP. | [6 empty] | X |  |  | continue to support; CTDOT has updated guidance on website
|  | Improvements in automotive technology. | Ignition interlocks for new drivers and/or repeat speeding offenders. | X | [7 empty] | X | needs legislative support
|  |  | Use of connected infrastructure (CI). | X | [7 empty] | X | costs could be challenging
|  |  | Incorporate the use of proven technology and roadway designs that make roadways safer |  |  |  | X (NHC) |  |  |  |  | X | needs further investigation
|  |  | Encourage auto manufacturers to install lane departure warning technology on all new vehicles |  |  |  |  | X |  |  | X |  | already installed in some vehicles
|  | Promotion of smartphone applications that monitor speeds and provide feedback. | In SHSP. | [8 empty] | X | needs further investigation
|  | RTSPs. | In SHSP. | [6 empty] | X |  |  | first plans were completed for all Regions; some COGs are in the process of conducting more
|  | Review design practices on non-safety projects to strengthen the analysis of safety data. | In SHSP. | [8 empty] | X | continue to support safety improvements on all highway projects whether using safety monies; collect data to help with the determination of effectiveness.
|  | Evaluate Safe Systems Approach to ensure integration of its principals into CTDOT designs. | In SHSP. | [7 empty] | X |  | needs further investigation, training, and policies
|  | Expand and utilize Safety Circuit Rider Programs. | Utilize established regional and state programs, such as the Safety Circuit Rider, to provide education, training, and outreach about intersection safety. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  | X |  |  | continue to support the T2 center to assist municipalities
|  | Equity analysis of equity stakeholder inclusion. | In SHSP. | [8 empty] | X | need more data and community input
HOW?
HOW?
WHEN?

## INTERSECTION RELATED
INFRASTRUCTURE EA: INTERSECTION RELATED
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Intersection Related Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSIP 21-24 Implementation Plans | Vision Zero | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of intersection-related fatalities and serious injuries to less than 655 by 2026. | Reduce fatal and serious-injury crashes at signalized intersections. | Install flashing yellow arrows. | Flashing yellow arrow installation | X |  |  |  |  | X | X |  |  | Safety tech brief being put out by T2 Center: Includes examples of where they have been installed; provides an educational standpoint to share information. Being considered in state project on Silas Deane Highway: Use flashing yellow arrow instead of traditional "dog-house".
|  |  | Berlin Turnpike pilot flashing yellow arrow location - evaluate effectiveness | X | [6 empty] | X |  | time needed to evaluate effectiveness
|  | Provide permissive to protected phasing. | Remove nighttime flash at signalized intersections study. |  | X | [5 empty] | X |  | underway. Will take time to complete and analyze impacts of removal.
|  |  | Removal of flashing period from all state intersections. | X | [5 empty] | X |  |  | underway, but will take time to complete at state and municipally-owned signals
|  |  | Change left turn phase from permissive to protected/permissive phasing on one or more approaches. | X | [6 empty] | X |  | being considered as traffic signals are designed
|  | Optimize clearance intervals. | Support Municipal Clearance Interval Project | X | X |  |  |  | X | X |  |  | Calculating and retiming yellow, all-red and pedestrian clearance intervals to minimize driver’s dilemma zone, reduce red light running and ensure compliance with MUTCD. 700+ Locations at Municipally-Owned Signals in 35 Municipalities Currently in Design; Installation in 2025. Design Completed & Installation On-Going at ~2,000 State-Owned Signals.
|  |  | Increase all red clearance intervals | X | [7 empty] | X | needs further investigation
|  |  | Increase total change interval | X | [7 empty] | X | needs further investigation
|  |  | Increase yellow change interval | X | [7 empty] | X | needs further investigation
|  |  | Use detection algorithms to extend vehicle clearance time. | X | [7 empty] | X | needs further investigation
|  | Eliminate turning movements. | Consider No Turn on Red restrictions at identified crash locations. |  |  |  | X (CR, METRO, NHC, NV, SC, WEST) |  |  |  | X |  | needs further investigation and data collection
|  | Provide signal coordination. | Traffic signal change interval re-timing. |  | X |  |  |  |  | X
|  |  | Traffic signal safety improvements. |  | X |  |  |  |  | X |  |  | projects in design
|  |  | Use of connected infrastructure (CI) | X | [7 empty] | X | Initial installation on Berlin Tpke; need time to evaluate; challenges include cost and evaluation of advances in technology
|  |  | Implement proven and low-cost spot and systemic safety improvements to reduce intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  | X |  | needs time to investigate further to provide signal coordination
|  |  | Provide coordinated signals to optimize traffic flow and reduce red-light running instances |  |  |  |  | X |  |  | X |  | signal system projects are being designed; will take time to upgrade timing for all coordinated signals
|  | Provide/adjust pedestrian phasing and timing. | Traffic signal pedestrian change interval re-timing. |  | X |  |  |  |  | X | X | X | continue to support as signals are designed
|  |  | Pedestrian signal heads with countdown timer installation. | X | [5 empty] | X | X | X | continue to support as signals are designed; takes time to program and design
|  | Convert intersection to roundabout. | Roundabout study |  | X |  |  |  |  | X |  |  | study underway
|  |  | Promote project funding and selection of regional improvement projects that convert existing signalized intersections into single lane roundabouts. |  |  |  | X (CR) |  |  |  | X |  | needs further investigation
| Reduce angle and turning crashes. | Restrict crossing U-turns. | Implement proven and low-cost spot and systemic safety improvements to reduce intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  |  | X | needs time to investigate and develop further for this application
|  | Provide left-turn and/or right-turn channelization. | Analyze findings from road diet studies and implement road diets. | X |  |  |  |  | X |  | X |  | Assessment of Road Diet Feasibility on Four-Lane Undivided Roadway Segments State-Owned Road Study Completed in 2018 (70 Segments) – 1 Segment in Waterford Installed; 1 Segment in Fairfield in Design Municipally-Owned Road Study On-Going (66 Segments); takes time to program, including gaining public support and coordinate with paving projects if possible
|  |  | Road diet installation from Rennell Dr to 250' East of North/South Line Creek Rd in Fairfield |  | X |  |  |  |  | X |  |  | project programmed
|  |  | Implement proven and low-cost spot and systemic safety improvements to reduce intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  | X |  | needs further investigation for this application
|  |  | Remove right turn slip lanes. |  |  |  |  | X |  |  |  | X | needs further investigation and then time to develop designs for implementation
|  | Improve bike and pedestrian facilities. | Traffic calming improvements, such as road diets to slow vehicle speeds, and integration of bike lanes and mixed/shared used infrastructure. |  | X |  |  |  |  | X |  |  | continue to support
|  |  | Provide crosswalk enhancements. |  |  |  |  | X |  | X | X | X | can be installed in near term and planned for long-term
|  | Use acceleration/merge lanes for left-turn movements from the cross street to keep free-flow operations in one direction on the arterial. | In SHSP. | [8 empty] | X | need time to investigate appropriate locations to implement
| Improve driver awareness at signalized intersections. | Install 12-inch LED lenses. | In SHSP. | [6 empty] | X |  |  | continue to support; already being done as traffic signals are designed and upgraded
|  | Provide signal head backplates. | Install signal head backplates with retroreflective borders when signals designed and upgraded. | X | [5 empty] | X | X | X | continue to support; already being done as traffic signals are designed and upgraded
|  |  | Add retroreflective border to existing signal backplates | X | [5 empty] | X |  |  | can be done; however only limited number of locations where backplates exist without retroreflective border
|  | Educate the public to improve understanding of traffic control devices. | Conduct high-visibility enforcement, media campaigns, and public outreach at locations with a significant number of intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  |  |  | X | need time to develop materials
|  | Mast arms with street names. | In SHSP. | [8 empty] | X | need time to develop policy changes; including maintenance agreements
|  | Increase training | Advertise and promote the Safety Circuit Rider and other similar programs that provide training and outreach about intersection safety. | X |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  | X | X |  | ongoing and can be further developed
| Improve driver compliance and access management. | Install red-light running cameras. | Installation of automated enforcement for red light running and speeding; CTDOT issued guidance | X |  | X (Sec. 16) |  |  | X | X |  |  | legislation already in place; municipalities working toward implementation
|  |  | Install red light running cameras for "Do Not Block the Box" intersections. |  |  |  |  | X |  |  |  | X | consider this as program/legislation developed in the future
|  | Confirmation lights for red-light running. | Use of connected infrastructure (CI). | X | [7 empty] | X | Initial installation on Berlin Tpke; need time to evaluate; challenges include cost and evaluation of advances in technology
|  | Restrict access to properties. | In SHSP. | [8 empty] | X | challenge includes property owner access rights; difficult to require for private property owners
|  | Restrict cross-median access. | In SHSP. | [8 empty] | X | challenge includes rights-of-way and access for other movements at adjacent intersections
|  | Install driveway closures when necessary. | Reduce driveway density | X | [7 empty] | X | challenge includes property owner access rights; difficult to require for private property owners
|  | Provide clear sight triangles. | Check sight lines and consider tree trimming as needed. |  |  |  | X (SC) |  |  |  | X |  | challenge to study and determine locations of concern and many items in sight triangles including many existing trees
| Reducing fatal and severe crashes at unsignalized intersections. | Install left-turn/offset left-turn lanes. | Improve left-turn lane offset to create positive offset. | X | [7 empty] | X | need time to further investigate to determine locations where effective
|  | Provide acceleration lanes. | In SHSP. | [8 empty] | X | need time to study and design where appropriate
|  | Install right-turn/offset right-turn lanes. | In SHSP. | [8 empty] | X | need time to study and design where appropriate
|  | Close median openings. | In SHSP. | [8 empty] | X | need time to study and design where appropriate
|  | Realign intersection approaches. | Realign intersection @ East Farm & N Walnut Streets and other intersection spot safety improvements |  | X |  |  |  |  | X |  |  | projects already programmed
|  | Restrict crossing U-turn. | In SHSP. | [8 empty] | X | need time to study and design where appropriate
|  | Close intersections. | In SHSP. | [8 empty] | X | need time to study and design where appropriate
|  | Improve geometry with a skew or radial T. | Widening and geometric revisions. |  | X
|  | Improve geometry with a skew or radial T. | Widening and geometric revisions. |  | X |  |  |  |  | X |  |  | spot location designs underway
|  |  | Improve angle of channelized right turn lane | X | [6 empty] | X |  | needs further investigation
| Improve driver awareness and operations at unsignalized intersections. | Install signing and pavement markings such as warning signs and doubling up of signing. | Support unsignalized intersection improvement projects: Signing and pavement marking improvements at state and municipally owned unsignalized intersections. | X | X |  |  |  | X | X |  |  | Projects underway; Installations are Increasing Awareness of Intersections – Municipal/Public Feedback Close to 700 Locations at Municipally-Owned Intersections in 60 Municipalities Currently in Design; Installation in 2024 to 2026 Design Completed & Installation On-Going at 600+ State-Owned Intersections in 105 Municipalities
|  |  | Replacement of speed limit and stop signs on municipal roadways study. |  | X |  |  |  |  | X |  |  | study underway; project to be implemented to install them.
|  |  | Wider edge lines/recurring pavement marking study. |  | X |  |  |  |  | X |  |  | study underway; project to be implemented to install them.
|  |  | Addition of edgelines and centerlines at RR crossings. | X | [5 empty] | X |  |  | continue to support
|  |  | Implement proven and low-cost spot and systemic safety improvements to reduce intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  | X | X | X | Various treatments
|  |  | Implement other systemic signing and pavement marking improvements | X | [7 empty] | X | need to investigate further
|  |  | Install advanced yield or stop markings/signs. | X | [5 empty] | X |  |  | can be installed where deemed appropriate
|  |  | Limit sign pollution. |  |  |  |  | X |  |  |  |  | need time to investigate concern
|  | Provide adequate street lighting. | Illumination study | X | [6 empty] | X |  | study underway. Analysis of study findings to be done.
|  |  | Provide intersection illumination. | X | [7 empty] | X | need to further investigate and challenge of who will install and maintain
|  | Install LED stop signs. | Implement proven and low-cost spot and systemic safety improvements to reduce intersection crashes. |  |  |  | X (CR, METRO, NEC, NHC, NV, RIVER, SC, WEST) |  |  | X | X | X | Various treatments
|  | Install dynamic feedback signs. | Speed feedback signs offered to all and provided to most municipalities and tribal owned roadways through T2 center. Data analysis to follow on effectiveness. | X | [6 empty] | X |  | data analysis needed to study effectiveness
|  |  | Install dynamic signal warning flashers | X | [7 empty] | X | need time to investigate further
|  | Install dynamic intersection conflict warning systems. | In SHSP. | [7 empty] | X |  | at least one location where installed in Woodbridge; challenge is time to determine appropriate locations and then design
|  | Provide urbanization approaches. | In SHSP. | [8 empty] | X | needs time for further investigation
|  | Install roundabouts. | Implement recommendations from Statewide Roundabout Study | X |  |  |  | X |  |  |  | X | Screen High Crash Locations on State Roadways for Potential Roundabout Installation. 600 Locations, 50 Viable Locations, 10 Conceptual Plans. Currently in Operational Analysis Phase (100 Locations); challenges include time to design and public outreach.
|  | Install all-way stops. | In SHSP. | [8 empty] | X | need time to investigate appropriate locations
| Additional strategies not part of the SHSP. | Intersection Control Evaluation (ICE) policy implementation. |  | X |  | X |  |  | X | X |  |  | Vision Zero Council recommendation By July 1, 2024, CTDOT must adopt a policy to use when it evaluates new intersections or modifications to existing intersections Work sheets and directive are being drafted to provide guidance
|  | Over-height vehicle detection system installation. |  |  | X |  |  |  |  | X |  |  | Projects in place.
|  | Quick build project and policy implementation | [5 empty] | X |  |  | X |  | Draft directive has been created. Challenge will be time to develop appropriate treatments at appropriate locations.
|  | Integrate variable speed limits. | [5 empty] | X |  |  |  | X | need to develop policies and gain legislative support
HOW?
HOW?
WHEN?

## x2 (hidden)
STRATEGY 4: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x3 (hidden)
STRATEGY 6: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x4 (hidden)
STRATEGY 9: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x5 (hidden)
STRATEGY 10: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x6 (hidden)
STRATEGY 11: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?