## PEDESTRIAN
PEDESTRIAN EA
Objective | SHSP Key Strategies |  | Activities and Initiatives to reduce Pedestrian Crashes | Activity/Initiative Source (if none then in 2022-2026 SHSP) |  |  |  |  | Recommended for Implementation by EA Team | Activity Implementation Timeline |  |  | Challenges with Implementation & Notes
|  |  |  | EA Team Meetings | HSIP Implementation Plan (FFY21-24) | Vision Zero | RTSP (COGs) | Summit |  | Near-term | Mid-term | Long-term
Decrease the five-year rolling average of pedestrian fatalities and serious injuries to less than 263 by 2026. | Reduce pedestrian exposure: | Sidewalk Improvements | Community connectivity grants. | X |  |  |  |  | X | X |  |  | program ongoing
|  | Accessible Pedestrian Signals | Install pedestrian signals for all traffic signals being upgraded (state owned). |  | X | [6 empty] | X | state needs time for design
|  |  | Install pedestrian signals for all traffic signals being upgraded (town owned). | X | [7 empty] | X | towns need time to program and design
|  |  | ADA compliance survey completed for municipalities gauging compliance; recommendations to come fall 2024 | X | [6 empty] | X |  | once recommendations completed can consider projects to implement
|  | Pedestrian Bridge/Tunnel Installation | Consider infrastructure improvements such as pedestrian bridges, bump outs, and filling in sidewalk gaps. |  |  |  |  | X |  |  |  | X | needs time to plan
|  | Install Countdown Timers | Add exclusive pedestrian phasing. | X | [7 empty] | X | need time to plan and design
|  | Leading Pedestrian Interval (LPI) | Clearance interval projects (District 2 & 4) |  | X |  |  |  |  | X |  |  | near term - already programmed; LPI could be considered
|  |  | Increase length of time of signal phases | X | [7 empty] | X | need further study if and where LPI may be appropriate
|  |  | Retime yellow and red clearance intervals as part of the municipal clearance interval project. | [5 empty] | X |  |  |  | Ensure funding needs are met to support pedestrian infrastructure improvements and associated maintenance costs.
|  | Road diets | Road Diet Fairfield (New Initiative) |  | X |  |  |  |  | X |  |  | design is being completed
|  |  | Road Diets (District 3) |  | X | [6 empty] | X | State study is finished; ongoing town study
|  |  | Implement road diets. |  |  |  |  | X |  |  |  | X | design and public process will take time
|  | Update policy to make LPI and other proven safety countermeasures as "standard" treatments in CT on all projects | In SHSP | [8 empty] | X | will take time to do this
|  | Pedestrian Refuge Islands | in SHSP | [8 empty] | X | will take time to determine locations with state jurisdiction; can be considered in spot improvement projects.
|  | Curb Extensions | in SHSP | [8 empty] | X | can be considered in spot improvement projects
|  | Additional Strategies not in SHSP | Identify key locations for No Turn on Red (NTOR) & blank out sign installation. | X |  |  |  |  | X |  |  | X | will take time to determine locations at state-owned intersections and then design and build; municipalities can program at any time
|  |  | Integrate protected left-turn signal phasing to reduce exposure to left turning traffic. |  |  |  |  | X |  |  |  | X | it will take time to determine where this would be appropriate, program, design, and construct
|  |  | Follow the pedestrian strategies and projects outlined in the Active Transportation section of MetroCOG’s Metropolitan Transportation Plan 2019-2045. |  |  |  | X (METRO) |  |  | X | X | X | some may take longer than others to implement
Decrease the five-year rolling average of pedestrian fatalities and serious injuries to less than 263 by 2026. | Improve visibility for pedestrians. | Crosswalk Enhancement | Complete state-wide network screening for locations where raised crosswalks and intersections should be prioritized, and program locations for raised feature installations. | X |  |  |  |  | X |  | X |  | municipalities can program and install on their roadways or by encroachment permit on state roadways.
|  |  | Midblock Crosswalk Upgrades (RRFBs) (Districts 1, 2, 3, & 4) |  | X |  |  |  |  | X |  |  | ongoing
|  |  | Pedestrian Improvements @ Signalized Intersections |  | X | [6 empty] | X | design underway at some intersections; long-term to address all intersections
|  |  | Pedestrian Signing Project |  | X |  |  |  |  | X |  |  | ongoing
|  |  | Traffic Signal Replacements for APS Upgrades (Districts 3 & 4) |  | X | [6 empty] | X | design underway; will take time to program, design, and install at other locations and in conjunction with equipment upgrades
|  |  | Install raised medians | [8 empty] | X | will take time to program, design, and implement
|  |  | Provide in-street pedestrian crosswalk signs. |  |  |  |  | X |  | X |  |  | municipalities can do this now through an encroachment permit
|  |  | Install embedded pavement lighting at crosswalks. |  |  |  |  | X |  |  | X |  | will take time to study available products and locations in CT.
|  |  | Install yield to pedestrian bollards - consider same as in-street ped crossing signs |  |  |  |  | X |  | X |  |  | municipalities can do this now through an encroachment permit
|  |  | Implement parking/landscaping restrictions to reduce parking near crosswalks. |  |  |  |  | X |  |  |  | X | there is a state law about parking at approaches to intersections; consider further legislation for crosswalk approaches, including midblock crosswalks
|  |  | Coordinate with CTDOT on the Pedestrian Signing and Pavement Marking Project which improves crosswalk visibility on local roads. |  |  |  | X (CR, METRO, NEC, NH, RIVER, SC, WEST) |  |  |  |  | X | COG to coordinate
|  | Crosswalk Illumination | Retro-actively install illumination at existing crosswalk locations on the state highway system via projects within the area, VIPs, maintenance (DAS) contracts, etc. | X |  |  |  |  | X |  |  |  | Time to integrate into projects and implement.
|  |  | Evaluate crosswalk illumination study to identify installation locations and typical treatments to implement. | X | X |  |  |  | X |  |  | X | using results from the study when complete to program locations, then design and implementation
|  | Eliminate screening by physical objects. | In SHSP | [8 empty] | X | need time to study further to understand where this may be a safety concern and how to address
|  | Provide pedestrian hybrid beacon (PHB). | Install pedestrian hybrid beacon (PHB or HAWK) | X |  |  |  | X |  |  |  | X | time to study appropriate locations and design with public input
|  | Provide/install rectangular rapid flashing beacon pedestrian crosswalk system (RRFBs). | Midblock Crosswalk Upgrades (RRFBs) (Districts 1, 2, 3, & 4) |  | X |  |  |  |  | X |  |  | ongoing
|  |  | Install RRFBs at unsignalized, high volume pedestrian crossing locations. |  |  |  |  | X |  | X |  |  | ongoing projects in design and construction
|  | Install crosswalks at roundabouts. | In SHSP | [6 empty] | X |  |  | this is being done when a roundabout is installed
|  | Evaluate and improve access at transit stops. | Promote transit as an option to non-motorized users. | X |  |  | X (WEST) |  |  |  |  | X | need to coordinate with Dep. Of Education
|  | Adding sidewalk connectivity and accessibility to/from transit stops. | Maintain pedestrian crosswalk at midblock locations | X | [5 empty] | X |  |  | performed by state or municipal maintenance
|  |  | Ensuring sidewalks are cleared for pedestrians in all weather conditions. |  |  |  |  | X |  |  |  | X | sidewalk maintenance under local jurisdiction - needs to be addressed by local enforcement/policy in areas of concern/as needed
Decrease the five-year rolling average of pedestrian fatalities and serious injuries to less than 263 by 2026. | Improving awareness for pedestrian safety. | Enforcement campaigns. | Automated enforcement (P.A. 23-116) | X |  | X |  |  |  | X |  |  | bill passed - municipalities working on
|  |  | Increased Law Enforcement funding. | X | [7 empty] | X | time to investigate funding sources
|  |  | No Turn on Red Implementation |  | X | [6 empty] | X | ongoing study
|  |  | Coordinate bike and pedestrian safety messages with agencies such as DMV, AAA CT Chapter, state and local law enforcement, emergency management services. |  |  |  | X (METRO, NH) |  |  |  | X |  | share information
|  |  | Encourage the region and State to join the road traffic safety project VISION ZERO. |  |  |  | X (NH) |  |  | X |  |  | already being done
|  | Education, outreach, and training. | Continued support towards pedestrian awareness campaigns out of the Highway Safety Office (HSO) and other advocacy groups (Safe Routes to School, Watch for Me CT, BikePed Advisory, T2 Center) | X |  |  |  |  | X | X |  |  | continue sharing of information and funding for campaigns
|  |  | Provide concurrent pedestrian phasing outreach and education. | X |  |  |  |  | X |  | X |  | some information already developed - need to investigate additional ways to provide educational resources
|  |  | Continued support of Community Connectivity Grants | X |  |  |  |  | X | X |  |  | program ongoing with increased funds
|  |  | Every other license renewal you must watch video on new traffic laws/controls/technology. |  |  | X (Sec. 7) |  |  |  | X |  |  | bill passed - video being developed
|  |  | Increased Safe Routes to School education for youths and young drivers. | X | [5 empty] | X |  |  | program ongoing
|  |  | Promote the Watch for Me CT Program. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | ongoing. Help promote when possible.
|  |  | Educate regional law enforcement personnel on the 2014 Vulnerable User Law and the 2015 Bike Bill. |  |  |  | X (CR, METRO, NEC, NH, NV, SC, WEST) |  |  |  | X |  | ongoing. Help promote when possible.
|  |  | Regionally promote the CT Bike Ped Plan interactive bike map. |  |  |  | X (CR, METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  |  | X |  | ongoing. Help promote when possible.
|  |  | Promote NHTSA’s Walk and Bike Safely Curriculum and Tips for stakeholders |  |  |  | X (METRO) |  |  |  | X |  | ongoing - need to investigate further
|  |  | Distribute the Connecticut Bicycle and Pedestrian Board’s Police Officer Handout about the state’s bike law to local law enforcement agencies. |  |  |  | X (METRO, NH) |  |  |  | X |  | ongoing - need to investigate further
|  |  | Regionally promote Traffic Skills 101 Bicycle Skills Classes. |  |  |  | X (METRO, NH) |  |  |  | X |  | need to investigate further
|  |  | Promote the Connecticut Technology Transfer Center’s outreach initiatives |  |  |  | X (METRO, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | ongoing
|  |  | CT DOT, CT Board of Education, & DMV to award "Vision Zero" program distinction to local and regional boards of education that offer a program teaching the mission of Vision Zero to students grades 6-12. |  |  | X (Sec. 3) |  |  |  | X |  |  | bill passed - help promote when possible
|  |  | Commissioner to develop a video outlining the current state laws that impact motorists, pedestrians, and bicyclists along with ways to practice safe driving. |  |  | X (Sec. 5) |  |  |  | X |  |  | need to investigate further
|  |  | Promote the NE CT Regional Engineering Program |  |  |  | X (NEC) |  |  |  | X |  | specific to one region
|  |  | Promote the regional pedestrian and bike projects included in the Transportation Improvement Program (TIP) 2021 - 2024. |  |  |  | X (RIVER) |  |  |  | X |  | specific to one region - consider for others
|  |  | Spreading awareness on high visibility clothing and the difficulties of seeing pedestrians in dark colored clothing. |  |  |  |  | X |  |  | X |  | consider for future campaigns
|  |  | Increasing access to pedestrian safety information and materials. |  |  |  |  | X |  |  |  | X | need to investigate further
|  |  | Ensuring pedestrian safety curriculum is taught in schools. |  |  |  |  | X |  |  |  | x | need to investigate further
|  |  | Providing educational classes tailored towards older pedestrians. |  |  |  |  | X |  | X |  |  | AAA offers classes
|  |  | Utilizing local, state, and federal advocacy groups to promote pedestrian safety. |  |  |  |  | X |  |  | X |  | ongoing
|  | Pedestrian safety audits (PSAs). | Support for continued implementation of Road Safety Audits (RSAs), emphasizing pedestrian safety. | X |  |  |  |  | X | X |  |  | Focusing on areas with high crash frequencies and pedestrian/bicycle safety concerns.
|  | Education campaigns in high-risk communities | Providing pedestrian accessibility improvements and implementing upgrades per ADA transition plan. | X |  |  |  |  | X |  | X |  | ongoing and additional projects once ADA transition plan complete
|  |  | Data analysis of disproportionately affected areas and equity using crash locations. | X | [6 empty] | X |  | needs more analysis
|  | Complete streets policies. | Implementation of the Intersection Control Evaluation (ICE) policy. | [5 empty] | X | X |  |  | Support including pedestrian related policies in the ICE as well as emphasizing pedestrians when evaluating new intersections or modifying existing intersections. Bill passed - more information to be distributed for implementation
|  |  | Encourage municipal and regional adoption of the CTDOT’s Complete Streets Policy. |  |  |  | X (CR, NEC, NH, NV, RIVER, SC, WEST) |  |  | X |  |  | ongoing
|  |  | Continue to update the Regional Pedestrian and Bike Plan and to follow the feasible action plan steps in the upcoming Complete Streets plan. |  |  |  | X (CR, METRO, NV, WEST) |  |  |  | X |  | ongoing
|  |  | Encourage departments involved in planning, programming, design, construction, retrofit, and maintenance to adopt CTDOT’s Complete Streets Policy related to local roads. |  |  |  | X (METRO) |  |  |  | X |  | ongoing
|  |  | Follow the recommendations in the 2019 Southeastern Connecticut Regional Bike and Pedestrian Plan. |  |  |  | X (SC) |  |  |  | X |  | specific to one region - ongoing
|  |  | Coordinate with State, regional, and local advocacy groups and bike store owners (BikeWalkCT CT, CT DOT Bike/Ped Advisory Board) to strategize best practices. |  |  |  | X (CR, METRO, NEC, NH. RIVER, SC, WEST) |  |  |  | X |  | COG suggestion ongoing
|  |  | Consider a Regional Pedestrian and Bike Plan. |  |  |  | X (WEST) |  |  |  |  | X | one COG suggestion
|  | Disallow plea bargaining for violations in pedestrian crossing laws. | In SHSP | [8 empty] | X | needs to be investigated further
|  | Data collection of pedestrian infrastructure elements and pedestrian exposure. | Evaluate the Pedestrian Crash Location study to identify systemic improvements that can be applied state-wide. Initiate projects or programs to provide improvements based on the pedestrian crash location study findings. | X | X |  |  |  | X |  | X |  | study started in 2024 - recommendations and strategies to be developed after study.
|  |  | Incentives for people to assist with crash information/video (dash cams, ring cams). Anonymous drop box? | X | [7 empty] | X | ideas need further development
|  |  | Idaho-Stop study |  |  | X |  |  |  | X |  |  | study completed - no opinion for or against study by CTDOT
|  |  | Encourage the adoption of the MMUCC 5th Edition to better collect data on bicycle facilities at crash locations. |  |  |  | X (NH) |  |  |  | X |  | one COG, but maybe others will do as well
|  | Renaming and updating the Highway Design Manual to reflect complete streets design. | In SHSP | [7 empty] | X |  | ongoing? Needs further investigation
Decrease the five-year rolling average of pedestrian fatalities and serious injuries to less than 263 by 2026. | Safe speeds or slowing vehicle strategies. | Install semi-diverters. | In SHSP | [8 empty] | X | needs further discussion by EAs
|  | Install speed humps, speed feedback signs, and/or chicanes. | UCONN T2 Center Speed Feedback Sign Installation in Towns/Municipalities. | X | [5 empty] | X |  |  | complete
|  |  | Uniform speed hump/bump design guide development for municipalities and identification of locations where implementation should be prioritized. | X | [7 empty] | X | needs further investigation. Identify locations where raised features should be prioritized.
|  | Provide full/partial diverters and street closure. | In SHSP | [8 empty] | X | needs further discussion
|  | Use/install speed tables/raised crosswalks. | Complete state-wide network screening for locations where raised crosswalks and intersections should be prioritized, and program locations for raised feature installations. | X |  |  |  |  | X | X |  |  | tech brief in development; municipalities can do now on own roads; municipalities can install on state roads with an encroachment permit
|  |  | Raised intersection study. |  | X | [5 empty] | X |  | ongoing
|  | Continue to allow municipalities to set speed limits and allow creation of pedestrian safety zones. | Implement automated enforcement for speed reduction and red-light running and study the effectiveness of automated enforcement to provide additional guidance to municipalities. | X |  |  |  |  | X | X |  |  | Specifically in areas with high pedestrian volumes, pedestrian safety zones, and/or school zones. Bill passed to allow municipalities to implement.
|  | Reduce statutory speed limits. | Increase the number of school zones with reduced regulatory speed limits. | X |  |  |  |  | X | X |  |  | municipalities can do now
|  |  | CT DOT developing design guidance on target speeds for projects. | X | [6 empty] | X |  | ongoing
|  |  | Decrease regulatory speed limits in areas with high volumes of pedestrian traffic. | X |  |  |  | X |  |  | X |  | municipalities can request to set their own speed limits
|  | Speed management training programs. | In SHSP | [8 empty] | X | needs further investigation
HOW?
HOW?
WHEN?

## x2 (hidden)
STRATEGY 4: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x3 (hidden)
STRATEGY 6: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x4 (hidden)
STRATEGY 9: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x5 (hidden)
STRATEGY 10: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed | Ongoing
[6 empty] | 1. | 2. | 3. | 4. | 5. | 6.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?

## x6 (hidden)
STRATEGY 11: Non-motorized Road Users
Objective | Strategy | Action Steps | Daily Activities | Task Tracking
|  |  |  | Responsibility | Timeframe | Not Started | Underway | Early Progress | Substantial Progress | Completed
[6 empty] | 1. | 2. | 3. | 4. | 5.
Decrease pedestrian fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 32 combined pedestrian fatalities and serious injuries per year. Decrease bicyclist fatalities and serious injuries 15 percent over the five-year period of the SHSP (ending in 2021). This will result in preventing 10 combined bicyclist fatalities and serious injuries per year.
HOW?
HOW?
HOW?
HOW?